{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["6月30日会议内容"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"6月30日会议内容","index":0,"n_rows":33,"n_cols":6,"rows_kept":33,"cut":false,"hidden":false,"merged":[[8,2,9,2],[10,2,20,2],[26,2,27,2],[28,2,32,2],[33,2,34,2],[10,5,15,5]]}
[]
[null,"序号","模块","内容","结论","备注"]
[null,1,"聚焦补偿","“手动选择点”的功能需要增加","后续迭代开发完成","林工"]
[null,2,"执行速度","针对拼图的时间、聚焦的时间、计算需要的时间的需要有模拟测试和统计",null,"于总"]
[null,3,"软件扩展","一些预留功能，如权限、集中处理的接口需要有",null,"于总"]
[null,4,"规程中的执行流程","测量区域中的视场应该可以移动，考虑自动检测的通用性。默认中心对齐基础上增加一个可以手动移动视场的功能。",null,"孙总"]
[null,5,"图库模式","颗粒、检测颗粒、排序等从工具栏移出，换到对应的界面中。",null,"林工、孙总"]
[null,6,"菜单栏","清洁度中菜单内的工具项要求可以用户进行配置。通过metis自定义界面功能中进行统一配置","进行一下功能调研","于总"]
[null,7,"审计追踪功能（蔡司独有的）","修改后是否可以查询用户对规程中进行了设置的详细内容的记录","基础功能做完之后再加。接口需要预留","林工"]
[null,8,null,"报告中增加电子签名"]
[null,9,"其它","研发的时间结点要保证，争取提早。保质保量","出详细的时间计划表","于总"]
[null,10,null,"硬件协调问题，尽量提前，制定计划"]
[null,11,null,"主要开发人员去上海学习其它产品Jomesa和奥林巴斯软件的特点，调研软件问题，在我们产品中提升"]
[null,12,null,"上海特斯拉客户，了解需求"]
[null,13,null,"注意处理速度及准确性，关键性能指标列出来，如计算、扫描等处理的时间速度等。每个细节的性能的说明，是否可以完成等。用于体现卖点？","要求出文档"]
[null,14,null,"颗粒的成分？是否可以和电镜软件相连接？"]
[null,15,null,"硬件供应到货时间，曲红卫下周反映结果",null,"曲红卫"]
[null,16,null,"Jomesa等产品的处理速度等关键指标对比，由林工负责",null,"于总、孙总"]
[null,17,null,"快、准、操作简单、功能强大。至少有一项对客户来说最急需的，作为我们软件的主要努力的方向。突出产品的优势。",null,"皮总"]
[null,18,null,"奥林巴斯等软件二值化的时候，边拍边二值化进行分析，速度快一些。"]
[null,19,null,"一张偏光、明场一次，然后再做第二张，可以进行一次对比测试","进行测试对比是具体方式","林工"]
[null,20]
[null,21]
[null,22]
[null,23]
[null,24]
[null,25]
[null,26]
[null,27]
[null,28]
[null,29]
[null,30]
[null,31]