{"text_format":"2","workbook":"xlsx","n_sheets":15,"sheets":["Sheet1","1","2","3","4","5","6","7","8","9","10","11","12","13","14"],"not_rendered":{"charts":0,"images":21,"macros":0,"external_links":0,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":52,"n_cols":10,"rows_kept":52,"cut":false,"hidden":false,"merged":[]}
[]
[null,"序号","问题分类","问题描述","提出者","提出日期","修改者","对应日期","对应说明","状态"]
[null,1,"功能实现","柱状图区域可以再高一些，比如100-200像素","沙永刚","2022-08-01","王琦","2022-08-02","增加高度","修改完"]
[null,2,null,"点击项目存档按钮，没有弹出确认提示框（因为存档后不可再编辑，因此需要弹出确认框让用户确认）","沙永刚","2022-08-02","王琦","2022-08-03","增加系统对话框","修改完"]
[null,3,null,"没有任何颗粒信息时，下方表格不合理","沙永刚","2022-08-02","王琦","2022-08-03",null,"修改完"]
[null,4,null,"分级最后是否通过，评判不正确","沙永刚","2022-08-02",null,null,"请先确认问题10后测试"]
[null,5,null,"用户能用鼠标拖动改变Grid行高（需要规定，不可改变）","沙永刚","2022-08-02","王琦","2022-08-03",null,"修改完"]
[null,6,null,"当不同类型分级名称不完全相同时，柱状图横坐标标示错误","沙永刚","2022-08-02","王琦","2022-08-04",null,"修改完"]
[null,7,null,"图片来源-项目图库（测试时偏光和明场使用的是同一张大图）：滤膜覆盖率大于100%了","沙永刚","2022-08-02",null,null,"首先确认滤膜面积输入是否正确"]
[null,8,null,"切换颗粒类型Tab时，柱状图位置发生变化了（应固定）","沙永刚","2022-08-02","王琦","2022-08-04",null,"修改完"]
[null,9,null,"分级列表中内容可修改了（应不可手动修改）","沙永刚","2022-08-02","王琦","2022-08-04",null,"修改完"]
[null,10,null,"规程保存和读取的数据参数不一致","王琦","2022-08-03"]
[null,11,null,"需要追加一个是否存档表示项目","沙永刚","2022-08-30","王琦","2022-09-05",null,"修改完"]
[null,12,null,"是否通过，数据库已有保存，该画面是否有必要重新计算？","沙永刚","2022-08-30",null,null,"暂时不需要确认"]
[null,13,null,"列头缺少名称","沙永刚","2022-09-08","王琦","2022-09-09",null,"修改完"]
[null,14,null,"检测结果显示与通常设置中“检测结果默认显示”设置不一致","宋珊珊","2022-09-15","宋珊珊","2022-09-15",null,"修改完"]
[null,15]
[null,16]
[null,17]
[null,18]
[null,19]
[null,20]
[null,21]
[null,22]
[null,23]
[null,24]
[null,25]
[null,26]
[null,27]
[null,28]
[null,29]
[null,30]
[null,31]
[null,32]
[null,33]
[null,34]
[null,35]
[null,36]
[null,37]
[null,38]
[null,39]
[null,40]
[null,41]
[null,42]
[null,43]
[null,44]
[null,45]
[null,46]
[null,47]
[null,48]
[null,49]
[null,50]

{"sheet":"1","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"2","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"3","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"4","index":4,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"5","index":5,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"6","index":6,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"7","index":7,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"8","index":8,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"9","index":9,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"10","index":10,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"11","index":11,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"12","index":12,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"13","index":13,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"14","index":14,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}